## WP1
Management
| D1.1.1 Internal and external project website | D1.1.2 Periodic project reports
Partner | Effort (person months)
HASRIL | 2 | 2
BME | 0 | 0.5
FFZG | 0.2 | 0.5
IPIPAN | 0 | 0.5
ULODZ | 0 | 0.5
UBG | 0 | 0.5
IPUP | 0 | 0.5
IBL | 0 | 0.5
LSIL | 0 | 0.5
Actual | 2.2 | 6 | 8.2
Planned | 3 | 52 | 55
Effort rate | 73.33% | 11.54%
Completion rate | 100% | 25%

## WP2
Analysis and selection of language resources
| D2.2.1 Language Whitepaper | D2.2.2 Contacts database of stakeholders | D2.2.3 Report on resources (actually or potentially) available to the consortium | D2.2.4 Report on methodology and criteria for the selection of resources | D2.2.5 Report on resources of further interest
Partner | Effort (person months)
HASRIL | 2.5 | 0.5 | 0.8 | 0.6 | 0.3
BME | 0.3 | 0.1 | 0.6 | 0.4 | 0.1
FFZG | 2.5 | 0.8 | 0.5 | 0.3 | 0.2
IPIPAN | 2.7 | 0.7 | 0.5 | 0.3 | 0.2
UBG | 2 | 0.5 | 0.6 | 0.3 | 0.2
ULODZ | 1.5 | 0.3 | 0.2 | 0.3 | 0.2
IPUP | 0.5 | 0.5 | 0 | 0 | 0
IBL | 1.5 | 1 | 1.5 | 0.5 | 0.5
LSIL | 2.2 | 1 | 0.5 | 0.3 | 0.1
Actual | 15.7 | 5.4 | 5.2 | 3 | 1.8 | 31.1
Planned | 5 | 8 | 8 | 8 | 8 | 37
Effort rate | 314% | 67.5% | 65% | 37.5% | 22.5%
Completion rate | 100% | 50% | 33%

## WP3
Enhancing language resources
| D3.3.1 First batch of resources... | D3.3.2 Second batch of resources | D3.3.3 Third batch of language resources
Partner | Effort (person months)
HASRIL | 3 | 1 | 0.5
BME | 6 | 3 | 0
FFZG | 4 | 1 | 0
IPIPAN | 10.23 | 0.22 | 8.22
UBG | 8 | 1 | 0.5
ULODZ | 4.5 | 2 | 0.5
IPUP | 0 | 0 | 10
IBL | 9 | 3 | 2
LSIL | 6.5 | 1.5 | 0.2
Actual | 51.23 | 12.72 | 21.92 | 85.87
Planned | 117 | 235 | 87 | 439
Effort rate | 43.79% | 5.413% | 25.2%
Completion rate

## WP4
Cross-national collaboration and Pilot service
| D4.4.1 Metadata descriptions and other interoperability standards as agreed with META-NET and partner projects | D4.4.2 IPR principles and provisions as agreed with META-NET and partner projects | D4.4.3 First upload of language resources | D4.4.4 Second upload of language resources | D4.4.5 Third upload of language resources
Partner | Effort (person months)
HASRIL | 2 | 2 | 1 | 0 | 0
BME | 3 | 3 | 1 | 0 | 0
FFZG | 0.2 | 0 | 0 | 0 | 0
IPIPAN | 0.3 | 0.2 | 0 | 0 | 0
UBG | 0.2 | 0.1 | 0 | 0 | 0
ULODZ | 2 | 1 | 0 | 0 | 0
IPUP | 0 | 0.5 | 0 | 0 | 0
IBL | 0.3 | 0 | 0 | 0 | 0
LSIL | 0.2 | 0.2 | 0 | 0 | 0
Actual | 8.2 | 7 | 2 | 0 | 0 | 17.2
Planned | 20 | 18 | 10 | 10 | 10 | 68
Effort rate | 41% | 38.89% | 20% | 0% | 0%
Completion rate | 100% | 100%

## WP5
Outreach, awareness and sustainability
| D5.5.1 | D5.5.2 | D5.5.3 | D5.5.4
| Action plan | Awareness, mobilisation and dissemination actions - described in the annual reports | Sustainability strategy and plans beyond the end of the project | Dissemination material (posters, flyers, brochures, t-shirts…)
Partners | Effort (person months)
HASRIL | 2 | 6 | 1 | 2
BME | 0.2 | 0 | 0 | 0.5
FFZG | 3 | 2 | 0.5 | 1
IPIPAN | 0.2 | 0.3 | 0.1 | 0.3
ULODZ | 0 | 0.5 | 0 | 1
UBG | 0.1 | 0.3 | 0 | 0.1
IPUP | 0 | 0 | 0 | 0.3
IBL | 0.1 | 0.2 | 0 | 0
LSIL | 0 | 0.1 | 0 | 0
Actual | 5.6 | 9.4 | 1.6 | 5.2 | 21.8
Planned | 21 | 73 | 17 | 18 | 129
Effort rate | 26.67% | 12.88% | 9.412% | 28.89%
Completion rate |  |  |  | 50%