## Project information
Grant Agreement number | 271022
Project acronym | CESAR
Reporting period (e.g. 1, 2, …) | 2
Period start date | 1st February, 2012
Period end date | 31st January, 2013

## PM
Second accounting period
| Consortium |  | WP1 |  | WP2 |  | WP3 |  | WP4 |  | WP5 |  | TOTAL
| Nr | short name | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned
| 1 | HASRIL | 16 | 16 | 1.5 | 2 | 39 | 28 | 2 | 3.3 | 13.5 | 8 | 72 | 57.3
* | 2 | BME | 0.7 | 0.75 | 1.8 | 1.7 | 55.03 | 27 | 5.92 | 4 | 10.6 | 4 | 74.05 | 37.45
* | 3 | FFZG | 4 | 4.5 | 9 | 2.33 | 38.04 | 18 | 2 | 2 | 36 | 21.5 | 89.04 | 48.33
| 4 | IPIPAN | 1.7 | 0.75 | 1.9 | 2 | 118.88 | 41 | 7.73 | 4 | 15 | 8 | 145.21 | 55.75
| 5 | ULODZ | 2.19 | 0.75 | 1.3 | 1.4 | 17.11 | 17 | 2.92 | 2.5 | 7.46 | 3 | 30.98 | 24.65
| 6 | UBG | 1.5 | 0.75 | 2 | 2 | 29.5 | 22 | 2.7 | 2 | 8.5 | 5 | 44.2 | 31.75
| 7 | IPUP | 2.5 | 2.25 | 1 | 1 | 23.9 | 30 | 4.5 | 3 | 11 | 2.17 | 42.9 | 38.42
| 8 | IBL | 4 | 0.75 | 4 | 3.4 | 49 | 32 | 2.9 | 2.5 | 14.6 | 6.17 | 74.5 | 44.82
| 9 | LSIL | 1.2 | 0.75 | 0.7 | 2 | 15.8 | 13 | 3 | 3 | 8 | 5.33 | 28.7 | 24.08
| TOTAL |  | 33.79 | 27.25 | 23.2 | 17.83 | 386.26 | 228 | 33.67 | 26.3 | 124.66 | 63.17 | 601.58 | 362.55
First accounting period
| Consortium |  | WP1 |  | WP2 |  | WP3 |  | WP4 |  | WP5 |  | TOTAL
| Nr | short name | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned
| 1 | HASRIL | 12 | 12 | 4.5 | 4 | 19 | 28 | 4 | 2.7 | 8.5 | 14 | 48 | 60.7
| 2 | BME | 1.25 | 1.75 | 2.65 | 3.3 | 61.12 | 27 | 11.35 | 8 | 3.5 | 8 | 79.87 | 48.05
| 3 | FFZG | 3.4 | 3 | 5.6 | 4.6667 | 12 | 18 | 2.38 | 4 | 11.5 | 11 | 34.88 | 40.6667
| 4 | IPIPAN | 0.8 | 1.75 | 4.1 | 4 | 41.4 | 41 | 3.27 | 7 | 1 | 8 | 50.57 | 61.75
| 5 | ULODZ | 1 | 1.75 | 2.7 | 2.6 | 16.5 | 17 | 3 | 4.5 | 1.5 | 6 | 24.7 | 31.85
| 6 | UBG | 1 | 1.75 | 4 | 4 | 14.5 | 22 | 3.3 | 4 | 6.5 | 10 | 29.3 | 41.75
| 7 | IPUP | 2 | 2.25 | 1 | 1 | 30.1 | 24 | 0.5 | 2 | 1.5 | 10.3333 | 35.1 | 39.5833
| 8 | IBL | 1.5 | 1.75 | 6 | 6.6 | 21 | 31 | 3.6 | 4 | 3.2 | 11.3333 | 35.3 | 54.6833
| 9 | LSIL | 1.3 | 1.75 | 8.9 | 4 | 14.3 | 13 | 5 | 5 | 4 | 10.6667 | 33.5 | 34.4167
| TOTAL |  | 24.25 | 27.75 | 39.45 | 34.1667 | 229.92 | 221 | 36.4 | 41.2 | 41.2 | 89.3333 | 371.22 | 413.45
PM TOTAL
| Consortium |  | WP1 |  | WP2 |  | WP3 |  | WP4 |  | WP5 |  | TOTAL
| Nr | short name | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned
| 1 | HASRIL | 28 | 28 | 6 | 6 | 58 | 56 | 6 | 6 | 22 | 22 | 120 | 118
| 2 | BME | 1.95 | 2.5 | 4.45 | 5 | 116.15 | 54 | 17.27 | 12 | 14.1 | 12 | 153.92 | 85.5
| 3 | FFZG | 7.4 | 7.5 | 14.6 | 6.9967 | 50.04 | 36 | 4.38 | 6 | 47.5 | 32.5 | 123.92 | 88.9967
| 4 | IPIPAN | 2.5 | 2.5 | 6 | 6 | 160.28 | 82 | 11 | 11 | 16 | 24 | 195.78 | 117.5
| 5 | ULODZ | 3.19 | 2.5 | 4 | 4 | 33.61 | 34 | 5.92 | 7 | 8.96 | 9 | 55.68 | 56.5
| 6 | UBG | 2.5 | 2.5 | 6 | 6 | 44 | 44 | 6 | 6 | 15 | 15 | 73.5 | 73.5
| 7 | IPUP | 4.5 | 4.5 | 2 | 2 | 54 | 54 | 5 | 5 | 12.5 | 12.5033 | 78 | 78.0033
| 8 | IBL | 5.5 | 2.5 | 10 | 10 | 70 | 63 | 6.5 | 6.5 | 17.8 | 17.5033 | 109.8 | 99.5033
| 9 | LSIL | 2.5 | 2.5 | 9.6 | 6 | 30.1 | 26 | 8 | 8 | 12 | 15.9967 | 62.2 | 58.4967
| TOTAL |  | 58.04 | 55 | 62.65 | 51.9967 | 616.18 | 449 | 70.07 | 67.5 | 165.86 | 160.5033 | 972.8 | 776
Note on N7: 34,92 PMs more because we hired five young researchers whose PM is ca 30% of senior researcher's PM. We are above personnel budget for ca 4%.

## Costs
Second accounting period, planned (Project total-First period)
Short name | Personnel costs | Subcontracting | Other Specific direct cost | Indirect costs, 30% | Total cost | requested contribution | second year |  | 1st year | Total
[7 empty] | 90% | 10%
HASRIL | 266899 | 4315 | 34477 | 80069.7 | 385760.7 | 192881.35 | 353417.9 | 32342.8 | 261095.3 | 646856
BME-TMIT | 213596 | 5000 | 39028 | 64078.8 | 321702.8 | 160852.4 | 291809.9 | 29892.9 | 276155.2 | 597858
FFZG | 200200 | 14000 | 33711.89 | 60060 | 307971.89 | 153985.945 | 283691.04 | 24280.85 | 177647.11 | 485619
IPIPAN | 367493 | 5000 | 40402 | 110247.9 | 523142.9 | 261572.45 | 491725.9 | 31417 | 105197.1 | 628340
ULODZ | 157920.94 | 5000 | 39683.6 | 47375.282 | 249980.822 | 124990.411 | 234466.947 | 15513.875 | 60296.678 | 310277.5
UBG | 214693 | 13344 | 36049 | 64407.9 | 328493.9 | 164246.95 | 308194.9 | 20299 | 77486.1 | 405980
IPUP | 120918 | 5000 | 40006 | 36276.4 | 202200.4 | 101100.2 | 185580.2 | 16620.2 | 130203.6 | 332404
IBL | 276906 | 14000 | 35685 | 83071.8 | 409662.8 | 204831.4 | 383319.525 | 26343.275 | 117202.7 | 526865.5
LSIL | 66602 | 4010 | 30124 | 19980.6 | 120716.6 | 60358.3 | 109426.575 | 11290.025 | 105083.9 | 225800.5
total | 1885227.94 | 69669 | 329166.49 | 565569.382 | 2849633.812 | 1424816.406 | 2641633.787 | 208000.025 | 1310367.688 | 4160001.5
| 1885227.94 | 69669 | 329166.49 | 565568.382 | 2849632.812 | 1424819.406
Second accounting period, actual
Short name | Personnel costs | Subcontracting | Other Specific direct cost | Indirect costs, 30% | Total cost | requested contribution
if+ > = túlköltés
HASRIL | 266899 | 4315 | 35282 | 80068.7 | 386564.7 | 193282.35 | 401
BME-TMIT | 246890 | 1564 | 20553 | 74067 | 343074 | 171537 | 10684.6
FFZG | 208456 | 15516.21 | 59220.16 | 62535.8 | 345728.17 | 172864.085 | 18878.14
IPIPAN | 357562.51 | 3967 | 51333.01 | 107268 | 520130.52 | 260065.26 | -1507.19
ULODZ | 128037 | 13140 | 42467 | 38411 | 222055 | 111027.5 | -13962.911
UBG | 82191.9833 | 13600 | 19038.16 | 24656.595 | 139486.7383 | 69743.3692 | -94503.5808
IPUP | 135522 | 1931 | 14672 | 36276 | 188401 | 94200.5 | -6899.7
IBL | 276707 | 13854 | 34429 | 83012.1 | 408002.1 | 204001.05 | -830.35
LSIL | 72541.04 | 2544.08 | 39469.68 | 21762.312 | 136317.112 | 68158.556 | 7800.256
total | 1774806.5333 | 70431.29 | 316464.01 | 528057.507 | 2689759.3403 | 1344879.6702 | -79936.7358
Project, total - DoW
short name | Personnel costs | Subcontracting | Other direct costs | Indirect costs 30% | Total costs | Requested EC contribution 50%
HASRIL | 448400 | 14000 | 49936 | 134520 | 646856 | 323428
BME-TMIT | 420660 | 5000 | 46000 | 126198 | 597858 | 298929
FFZG | 326630 | 14000 | 47000 | 97989 | 485619 | 242808.5
IPIPAN | 441800 | 5000 | 49000 | 132540 | 628340 | 314170
ULODZ | 199445 | 5000 | 46000 | 59832.5 | 310277.5 | 155138.75
UBG | 264600 | 14000 | 48000 | 79380 | 405980 | 202990
IPUP | 216080 | 5000 | 46500 | 64824 | 332404 | 166202
IBL | 357205 | 14000 | 48500 | 107160.5 | 526865.5 | 263432.75
LSIL | 142155 | 5000 | 36000 | 42645.5 | 225800.5 | 112900.25
Total | 2816975 | 81000 | 416936 | 845090.5 | 4160001.5 | 2080000.25
First year, reported
short name | Personnel costs | Subcontracting | Other direct costs | Indirect costs 30% | Total costs | Requested EC contribution 50%
HASRIL | 181501 | 9685 | 15459 | 54450.3 | 261095.3 | 130546.65
BME-TMIT | 207064 | 0 | 6972 | 62119.2 | 276155.2 | 138076.6
FFZG | 126430 | 0 | 13288.11 | 37929 | 177647.11 | 88822.555
IPIPAN | 74307 | 0 | 8598 | 22292.1 | 105197.1 | 52597.55
ULODZ | 41524.06 | 0 | 6316.4 | 12457.218 | 60296.678 | 30148.339
UBG | 49907 | 656 | 11951 | 14972.1 | 77486.1 | 38743.05
IPUP | 95162 | 0 | 6494 | 28547.6 | 130203.6 | 65101.8
IBL | 80299 | 0 | 12815 | 24088.7 | 117202.7 | 58601.35
LSIL | 75553 | 990 | 5876 | 22664.9 | 105083.9 | 52541.95
Total | 931747.06 | 11331 | 87769.51 | 279521.118 | 1310367.688 | 655183.844

## HASRIL
Coordinator - HASRIL
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 266899 | salaries for 42 emloyees
| Subcontracting | 4315 | WS Hungary - for the organization of the Hungarian Road Show, dissemination
| Other Specific direct cost | 35282 | costs for travels (meetings, conferences) and equipment
| Indirect costs | 80068.7 | 30% of Personnel costs
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 386564.7
List of travels
WHO | WHERE
Paris, France | Dávid Takács
Luxembourg, Luxemburg | Tamás Váradi
Istambul, Turkey | Tamás Váradi
Trento, Italy | Tamás Váradi
Bratislava, Slovakia | Tamás Váradi
Bratislava, Slovakia | Tibor Pintér
Istambul, Turkey | Enik Heja
Bruxelles, Belgium | András Kornai
Bruxelles, Belgium | Tamás Váradi
Bruno, Czech Republic | András Beke
Bruxelles, Belgium | Piroska Lendvai
Warsaw, Poland | Tamás Váradi
Bruno, Czech Republic | Tamás Váradi
Sofia, Bulgaria | Piroska Lendvai
Sofia, Bulgaria | Tamás Váradi
Belgrade, Serbia | Tamás Váradi
Soeul, Korea | Tamás Váradi
Zagreb, Croatia | Tamás Váradi
szeged, Hungary | Tamás Váradi
szeged, Hungary | Csaba Oravecz
szeged, Hungary | Marton Mihaltz
Berlin, Germany | Tamás Váradi

## BME
BME
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 246890 | salaries for 34 people
| Subcontracting | 1564 | Audit fee
| Other Specific direct cost | 20553 | Travel costs, other costs
| Indirect costs | 74067 | 30% of Personnel costs
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 343074
List of travels
WHO | WHERE
Gyorgy Szaszak | Ireland
Gellert Sarosi | Ireland
Gyorgy Szaszak | Belgium
Geza Nemeth | Belgium
Peter Nagy | Austria
Geza Nemeth | England
Gyorgy Szaszak | Belgium
Klara Vicsi | Czech Republic
Gyorgy Szaszak | Czech Republic
Gyorgy Szaszak | Poland
Balazs Tarjan | Sweden
Geza Nemeth | Slovakia
Klara Vicsi | Slovakia
Gabor Kiss | Slovakia
Gyorgy Szaszak | Switzerland
Imre Viktor | Czech Republic
Geza Nemeth | Poland
Tibor Fegyo | Slovakia
Geza Nemeth | Croatia
David Sztaho | Slovakia
Geza Nemeth | Germany
Csaba Zainko | Slovakia
Eniko Csala | Slovakia
Balazs Tarjan | Slovakia
Tamas Csapo | Slovakia
Gellert Sarosi | Slovakia

## FFZG
FFZG
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 208456 | Senior researchers and researchers partial salaries (154.278,30), young researchers full salaries (45.177,70: Dasa Berovic, Danijela Merkler, Vanja Stefanec, Ivana Dobronic, Ana Agic), external consultant partial salary (9000,00: Max Silberztein)
| Subcontracting | 15516.21 | Invoices by agency Ulix for organization of Zagreb road-show
| Other Specific direct cost | 59220.16 | Travel (RTD and dissemination), equipment (3 laptops), dissemination material (design, production)
| Indirect costs | 62535.8 | 30% of personnel costs
| Remaining costs | 0
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 345728.17
List of travels
WHO | WHERE
Marko Tadić | Sofia, BG road-show preparation
Krešimir Šojat | Sofia, BG road-show preparation
Vanja Štefanec | Sofia, BG road-show preparation
Marko Tadić | Bruxelles, Y1 review
Marko Tadić | Sofia, BG road-show
Marko Tadić | Bratislava, SK road-show preparation
Krešimir Šojat | Istanbul, LREC2012
Daniela Katunar | Istanbul, LREC2012
Kristina Vučković | Istanbul, LREC2012
Marko Tadić | Trento, EAMT2012
Marko Tadić | Bratislava, SK road-show
Željko Agić | Paris, NooJ2012
Božo Bekavac | Paris, NooJ2012
Marko Tadić | Paris, NooJ2012
Marko Tadić | Bruxelles, META-FORUM2012
Vanja Štefanec | Cagliari, Between Antiquity and Modernity
Vanja Štefanec | Dubrovnik, FASSBL2012 preparation
Marko Tadić | Warsaw, PL road-show preparation
Marko Tadić | Mainz, SlavPCorp2012
Nikola Ljubešić | Mainz, SlavPCorp2012
Marko Tadić | Dubrovnik, FASSBL2012
Vanja Štefanec | Dubrovnik, FASSBL2012
Željko Agić | Dubrovnik, FASSBL2012
Danijela Merkler | Dubrovnik, FASSBL2012
Daša Berović | Dubrovnik, FASSBL2012
Daniela Katunar | Dubrovnik, FASSBL2012
Nikola Ljubešić | Dubrovnik, FASSBL2012
Ana Agić | Dubrovnik, FASSBL2012
Krešimir Šojat | Dubrovnik, FASSBL2012
Vanja Štefanec | Dubrovnik, FASSBL2012
Božo Bekavac | Dubrovnik, FASSBL2012
Marko Tadić | Warsaw, PL road-show
Marko Tadić | Ljubljana, IS-JT2012
Željko Agić | Ljubljana, IS-JT2012
Danijela Merkler | Ljubljana, IS-JT2012
Nikola Ljubešić | Ljubljana, IS-JT2012
Daša Berović | Ljubljana, IS-JT2012
Marko Tadić | Belgrade, SR road-show preparation
Marko Tadić | Sofia, CLARIN2012
Željko Agić | Sofia, CLARIN2012
Marko Tadić | Belgrade, SR road-show
Željko Agić | Belgrade, SR road-show
Božo Bekavac | Belgrade, SR road-show
Nikola Ljubešić | Ljubljana, research
Danijela Merkler | Mumbai, COLING2012
Željko Agić | Mumbai, COLING2012
Marko Tadić | Budapest, HU road-show
Damir Boras | Budapest, HU road-show
Nives Mikelić Preradović | Budapest, HU road-show
Božo Bekavac | Budapest, HU road-show
Marko Tadić | Berlin, META-SHARE2013
Božo Bekavac | Berlin, META-SHARE2013
Marko Tadić | Luxembourg, Y2 review
Božo Bekavac | Luxembourg, Y2 review

## IPIPAN
IPIPAN
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 357562.51 | salaries
| Subcontracting | 3967 | Road-show costs
| Other Specific direct cost | 51333.01 | Travel: 22868,79 EUR Equipment: 14994,07 EUR Dissemination: 13470,15 EUR
| Indirect costs | 107268
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 520130.52
List of travels
WHO | WHERE
Maciej Ogrodniczuk | Belgium, Brussel, 15-18 april 2012
Adam Przepiórkowski | Turkey, Stambul, 20-27 may 2012
Maciej Ogrodniczuk | Turkey, Stambul, 21-26 may 2012
Maciej Ogrodniczuk | Belgium, Brussel, 19-21 june 2012
Adam Przepiórkowski | Indonesia, Denpasar 20 june - 2 july 2012
Adam Przepiórkowski | South Korea, Jeju 07-15 july 2012
Katarzyna Krasnowska | Czech Republic, Brno, 03-07 september 2012
Adam Przepiórkowski | Czech Republic, Brno, 03-07 september 2012
Adam Przepiórkowski | Germany, Mainz, 09-12 september 2012
Bartosz Zaborowski | Japan, Kanazawa, 19-25 october 2012
Adam Przepiórkowski | Japan, Kanazawa, 20-25 october 2012
Maciej Ogrodniczuk | Croatia, Zagreb, 29 november-01december 2012
Jakub Waszczuk | India, Mombai, 07-15 december 2012
Adam Przepiórkowski | India, Mombai, 09-16 december 2012
Jakub Waszczuk | Poland, Warsaw, 12 december 2012
Agata Savary | India, Mombai, 10-16 december 2012
Maciej Ogrodniczuk | Hungary, Budapest, 18-19 january 2013
Maciej Ogrodniczuk | Luxembourg, 8-10 april 2013

## ULODZ
ULODZ
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 128037 | 30.98 PMs for 18 employees
| Subcontracting | 13140 | This part of the ULodz budget was increased at the expense of Personell costs (with prior permission of the project officer). All of the subcontracting funds were spent on the acquisition and enhancement of the SNUV speech database from Voicelab (a speech recognition company). The database is now available as one of the CESAR resources under the CC-BY license for academic and commercial use.
| Other Specific direct cost | 42467 | Travel: 16260.16, Equipment: 1674.93, Dissemination: 24531.61
| Indirect costs | 38411 | 30% of personnel costs
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 222055
List of travels
WHO | WHERE
Piotr Pęzik | Warsaw
Piotr Pęzik | Luxembourg
Piotr Pęzik | Istanbul
Łukasz Dróżdż | Istanbul
Piotr Pęzik | Warsaw
Mikołaj Deckert | Berlin
Maciej Buczek | Berlin
Piotr Pęzik | Berlin
Łukasz Dróżdż | Berlin
Piotr Pęzik | Warsaw
Piotr Pęzik | Brussels
Piotr Pęzik | Poznan
Piotr Pęzik | Warsaw
Piotr Pęzik | Brussels
Piotr Pęzik | Maribor, Slovenia
Maciej Buczek | Zagreb
Łukasz Drożdż | Zagreb
Piotr Pęzik | Zagreb
Łukasz Dróżdż | Budapest
Maciej Buczek | Budapest
Piotr Pęzik | Budapest

## UBG
UBG
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 82191.9833 | salareies for 12 persons
| Subcontracting | 13600 | 1. External expert (Max Silebrztein) - 9000 euros 2. University of Belgrade, Faculty of Mining and Geology - the usage of hardware for web services and maintenance- 4600 euros
| Other Specific direct cost | 19038.16 | 1. Treveling costs - 3699, 25 2. Equipment - 3684,05 3. Dissemination - 11654,86
| Indirect costs | 24656.595
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 139486.7383
List of travels
WHO | WHERE
Dusko Vitas | Brussels
Cvetana Krstev | Brussels
Dusko Vitas | Hamburg
Cvetana Krstev | Hamburg
Zorica Stanimirovic | Sofia
Krstev Cvetana | Amsterdam

## IPUP
IPUP
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 135522 | Personnel costs for the 42,90 PM used by 11 employees in the reporting period.
| Subcontracting | 1931 | Costs for organisation of dissemination event
| Other Specific direct cost | 14672 | Travel expenses, Dissemination materials, events and activities.
| Indirect costs | 36276
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 188401
List of travels
WHO | WHERE
Mladen Stanojevic | Brussel
Uros Milosevic | Paris
Mladen Stanojevic | Brussel
Natalija Kovacevic | Varsava
Mladen Stanojevic | Zagreb
Mladen Stanojevic | Budapest
Mladen Stanojevic | Luxemburg

## IBL
IBL
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 276707 | 34 employees for the period from different institutions - Institute for Bulgarian language, Sofia university, Plovdiv university and Tetracom LTD. Employees were from several different categories.- computational linguists, computer scientists, language researchers, and developers.
| Subcontracting | 13854
| Other Specific direct cost | 34429 | 9303.31 euro - traveling to attend Meta-Net events, Cesar roadshows, Cesar project meetings and dissemination activities; 12620.48 euro - equipment: servers 1 x HP DL160-G8, 1 x IBM System x3550 M3, 12704.90 euro - for room rental, catering, technical equipment for Cesar roadshow in Sofia, 02.05.2012, and following dissemination events at a national level, promotional materials, professional PR services for the period.
| Indirect costs | 83012.1
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 408002.1
List of travels
WHO | WHERE
Svetla Koeva | Sofia- Paris- Luxembourg-Paris- Sofia
Svetla Koeva | Sofia- Venice- Sofia
Svetla Koeva | Sofia-Vienna-Dubrovnik-Vienna-Sofia
Svetla Koeva | Sofia-Moscow-St.Petersburg
Svetla Koeva | Sofia-Budapest-Sofia
Svetla Koeva | Sofia-Vienna-Dubrovnik-Vienna-Sofia
Angel Genov | Sofia-Berlin
Svetla Koeva | Sofia-Berlin
Hristina Kukova | Sofia- Veliko Turnovo
Svetla Koeva | Sofia- Plovdiv- Sofia
Svetla Koeva | Sofia-Brussels-Sofia
Svetla Koeva | Sofia-Istanbul-Sofia
Cvetana Dimitrova | Sofia-Brussels-Sofia
Svetla Koeva | Sofia-Brussels-Sofia
Cvetana Dimitrova | Sofia- Düsseldorf- Warsaw- Sofia
Svetla Koeva | Sofia-Vienna-Belgrade-Sofia-Vienna
Svetla Koeva | Sofia-London-Dublin-London-Sofia
Svetla Koeva | Sofia-Vienna-Zagreb-Vienna-Sofia
Svetla Koeva | Sofia-Munich-Berlin-Vienna-Sofia
Cvetana Dimitrova | Sofia-Munich-Berlin-Vienna-Sofia
Svetla Koeva | Sofia-Brussels-Sofia

## LSIL
LSIL
Personnel, subcontracting and other major cost items
Work Packages | Item description | Amount | Explanations
| Personnel costs | 72541.04 | four part time senior researcher, six part time technical employees, one part time expert
| Subcontracting | 2544.08 | simultaneous interpretation during the roadshow event, design of dissemination materials (leaflets, posters), organization of roadshow event, compiling of Slovak language collocation by Lexical Computing
| Other Specific direct cost | 39469.68 | Computing and storage server, networked scanner, HDD's for data storage, various computing equipment, expendables, workshop and roadshow expenses, Slovak language whitepapers, travel expenses
| Indirect costs | 21762.312
Remaining costs
TOTAL COSTS AS CLAIMED IN FIANCIAL STATEMENT |  | 136317.112
List of travels
WHO | WHERE
R. Garabík | Brussels
A. Žáková | Sofia
K. Gajdošová | Sofia
A. Žáková | Warsaw
R. Garabík | Warsaw
A. Žáková | Zagreb
R. Garabík | Zagreb
R. Garabík | Budapest
A. Žáková | Berlin
R. Garabík | Berlin
R. Garabík | Luxembourg